## Sheet1
MPR
क्रम संख्या | विभाग का नाम | कार्य का नाम | शासनादेश संख्या एवं स्वीकृत धनराशि | अवमुक्त धनराशि | वित्तीय प्रगति | भौतिक प्रगति
1 | चिकित्सा एवं स्वास्थ्य सेवाएं | C.H.C. KARARI AT DISTRICT KAUSHAMBI | 28/2016/2822/5-6-16-127(NI.0)/12 DATED 27.01.2016 | 446 | 100 | 80
2 | चिकित्सा एवं स्वास्थ्य सेवाएं | P.H.C. SHAHPUR AT DISTRICT KAUSHAMBI | 188/2019/1320/5-6-19-26(NIRMAN)/18 DATED 15.07.2019 | 68 | 50 | 50
3 | अन्य सिविल कार्य | ADVOCATE CHAMBER BLOCK-A, AT DISTRICT PRAYAGRAJ | 150/2017/UO36/7-NYAY-9(BAJAT)-2017-20(SAMANYA)/2013-NYAY-7 DATED 27.12.2017 | 200 | 5 | 1
4 | अन्य सिविल कार्य | ADVOCATE CHAMBER BLOCK-B, AT DISTRICT PRAYAGRAJ | 02/2017/UO160/7-NYAY-9(BAJAT)-2016-20(SAMANYA)/2013-NYAY-7 DATED | 200 | 100 | 43
5 | अन्य सिविल कार्य | ADVOCATE CHAMBER BLOCK-C AT DISTRICT PRAYAGRAJ | 02/2017/UO160/7-NYAY-9(BAJAT)-2016-20(SAMANYA)/2013-NYAY-7 DATED | 468 | 100 | 100
6 | अन्य सिविल कार्य | 04 NOS. FAMILY COURT IN DISTRICT COURT CAMPUS PRAYAGRAJ | 133/2019/1040/7-NYAY-9(BAJAT)-2019-800(40)/2016 DATED 20.09.2019 | 482 | 18 | 9
7 | श्रम विभाग (व्यावसायिक शिक्षा एवं कौशल विकास) | I.T.I. SORAON AT DISTRICT PRAYAGRAJ | 120/2015/1602/89-VYA0SHI0 & KAU0VI0VI0-2015-05(PO)/2015 DATED 05.06.2015 | 550 | 100 | 76
8 | उच्च शिक्षा | D.I.E.T. KAUSHAMBI IN RENOVATION WORK | RASHAI0/4727-40/A-1(21)/2015-16 DATED 29.04.2015 | 104 | 100 | 100
9 | उच्च शिक्षा | D.I.E.T. PRAYAGRAJ IN RENOVATION WORK | RASHAI0/4803-52/2020-21 DATED 27.03.2020 | 11 | 1 | 1
10 | ग्राम विकास विभाग | DISTRICT PRAYAGRAJ IN VIKASKHAND KORAON RESIDENTIAL BUILDING | 27/2018/SA0/373/38-2-2018-17B/2017 DATED 22.03.2018 | 106 | 100 | 28
11 | पर्यटन | SHRI BHAIRAV BABA MANDIR IN MAHEWA CHAKA NAINI, PRAYAGRAJ | 173/2018/41-2018-21(BAJAT)/2018 DATED 05.10.2018 | 52 | 100 | 100
12 | पर्यटन | TEHSIL HANDIYA LAXAGRIH RENOVATION IN DISTRICT PRAYAGRAJ | 48/2019/675/41-2019-25(BAJAT)/2018 DATED 20.02.2019 | 100 | 100 | 50
13 | अन्य सिविल कार्य | TOILET & FALL CEILING IN RAJKIYA UNANI MEDICAL COLLEGE HIMMATGANJ | 14/2019/1307/96-AYUSH-1-2019-100/2019 DATED 09.03.2019 | 65 | 100 | 90
14 | अन्य सिविल कार्य | 04 LECTURE HALL IN L.B.S.H. IN SHANTIPURAM PRAYAGRAJ | 14/2019/668/96-AYUSH-2-2019-11(B)/2019 DATED 08.03.2019 | 92 | 65 | 23
15 | अन्य सिविल कार्य | GIRL HOSTEL IN L.B.S.H. IN SHANTIPURAM PRAYAGRAJ | 14/2019/668/96-AYUSH-2-2019-11(B)/2019 DATED 08.03.2019 | 77 | 100 | 35
16 | अन्य सिविल कार्य | BOYS HOSTEL IN L.B.S.H. IN SHANTIPURAM PRAYAGRAJ | 14/2019/668/96-AYUSH-2-2019-11(B)/2019 DATED 08.03.2019 | 93 | 44 | 15
17 | गृह | FIRE STATION PATHARTAL KORAON AT DISTRICT PRAYAGRAJ | 123/2019/506/6-PU0-7-2019-78/2019/GRIH(POLICE) ANUBHAG-7 DATED 26.06.2019 | 181 | 100 | 25
18 | गृह | FIRE STATION SIRATHU AT DISTRICT KAUSHAMBI | 124/2019/562/6-PU0-7-2019-83/2019/GRIH(POLICE) ANUBHAG-7 DATED 26.06.2019 | 358 | 89 | 38
19 | अन्य सिविल कार्य | VETERINARY HOSPITAL AT AJUHA KAUSHAMBI | 1107/37-2-2019-(35)/2014/PASHUPALAN/DATED 18.06.2019 | 40 | 47 | 47
20 | गृह | IV VAHINI PAC SEWER IN DISTRICT PRAYAGRAJ | 153/2019/1359/6-PU0-7-2019-31/2017 DATED 24.08.2019 | 320 | 100 | 50
21 | कारागार | CONTROL ROOM IN CENTRAL JAIL NAINI PRAYAGRAJ | 60/2019/905/22-4-2019-48(16)/19 DATED 25.10.2019 | 6 | 21 | 21
22 | ऐन.ऐच.ऐम | 111 NOS. GNM CENTER IN PRAYAGRAJ | CMO/WELLNESS CENTER/NIRMAN/2019-20/5508 DATED 19.09.2019 | 380 | 90 | 50
23 | खेलकूद/युवा कल्याण | MINI STADIUM TILGODI AT CHAIL, DISTRICT KAUSHAMBI | 456/50-YU0KA0-2020-17(GHOSANA)/2028 DATED 06.03.2020 | 125 | 4 | 1
24 | अन्य सिविल कार्य | VIKASKHAND CHAKA NITROJAL VESEL PHENSING | 1235/37-2-2018-6(4)2018 DATED 03.04.2018 | 2 | 100 | 100
25 | चिकित्सा एवं स्वास्थ्य सेवाएं | CONSTRUCTION OF PRIMARY HEALTH CENTRE AT VILLAGE-SIURA, DADROL DISTT- SHAHJAHANPUR | 184/2020/624-5-6-2020-38(NIRMAN)/19 DATE-13.08.2020, AMOUNT- 185.23 | 50 | 50 | 27
26 | चिकित्सा एवं स्वास्थ्य सेवाएं | CONSTRUCTION OF PRIMARY HEALTH CENTRE AT VILLAGE-BARAURA, TILHER DISTT- SHAHJAHANPUR | 58/2019/568/5-6-19-3(NIRMAN)/19 DATE-08.03.2019, AMOUNT- 185.23 | 47 | 47 | 34
27 | चिकित्सा एवं स्वास्थ्य सेवाएं | CONSTRUCTION OF PRIMARY HEALTH CENTRE AT VILLAGE- KHADWA DISTT- BAREILLY | 85/2020/309/5-6-2020-09(NI0)/2020 DATE-25.03.2020, AMOUNT- 195.57 | 47 | 47 | 24
28 | खेलकूद/युवा कल्याण | Construction of Multipurpose Hall Village Alahdadpur Aligarh | 29-103/ MYAS/MDASD/2018(1)/5405 Dated 20.12.2018 | 250 | 41 | 41
29 | खेलकूद/युवा कल्याण | Construction of Multipurpose Hall Village Rafatnagar Distt. Etah. | 29-100/ MYAS/MDASD/2018(1)/5163 Dated 06.12.2018 | 150 | 33 | 33
30 | पर्यटन | Construction of Nagla Chandrabhan Distt. Mathura. | 41/2017/1762(1)/41-2017-06 (Bujat) Dated 15-09-2017 | 498 | 85 | 85
31 | पर्यटन | Construction of Chandra Kund Sanchauli Nandgaon Mathura. | 43/2019/86/41-2019-07 (Bajat) Dated 18-02-2019 | 261 | 86 | 86
32 | प्राविधिक शिक्षा | Construction of Rajikya Mahila Polytechnic Hardoi Distt. Aligarh | 2132/16-3-2017-30(B)/2017 Dated 18-01-2018 | 310 | 22 | 22
33 | माध्यमिक शिक्षा/बेसिक शिक्षा | Construction of Rajkiya Girls Inter Collage 5 Class Kasganj | BIP/117/15-10-14-3(Gho)/2014 Date 19-12-2017 | 27 | 50 | 50
34 | माध्यमिक शिक्षा/बेसिक शिक्षा | Construction Of Rajkiya High School Kathaira Aligarh | RMSA/5964-67/2017-18 Dated 28-08-2017 | 54 | 58 | 58
35 | चिकित्सा एवं स्वास्थ्य सेवाएं | CONSTRUCTION OF COMMUNITY HEALTH CENTER AT SHAHPUR BAMATA, DISTT- GHAZIABAD | 21/2016/2904/5-6-16-46(Nirman)/16, DATED 04.01.2017 | 429 | 100 | 72
36 | चिकित्सा एवं स्वास्थ्य सेवाएं | CONSTRUCTION OF 05 NOS. HEALTH & WELLNESS CENTRE (AROGYA KENDRA) AT BLOCK BHOJPUR, LONI AND MURAD NA | 2019-20/4065, Dated 24.07.2019 | 13 | 45 | 23
37 | अल्पंखयक कल्याण | CONSTRUCTION OF GOVT. INTER COLLEGE AT DEHRA, BLOCK DHAULANA, DISTT – HAPUR (U.P) | 428/52-1-2018-33(MSDP)/2018, Dated 02.02.218 | 228 | 100 | 50
38 | पर्यटन | JANPAD MAHOBA (CHARKHARI) KA PARYATAN VIKAS KARYA | 18/2019/100/41/-2019-160(BAJAT)/2018 Dt. 10-01-2019 | 62 | 100 | 100
39 | पर्यटन | JANPAD BANDA ME SIMAUNI BABA DHAM KA PARYATAN VIKAS KARYA | 2856/41-2018-78 (BAJAT)/2018 Dt. 01-10-2018 | 149 | 5 | 23
40 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVET. GIRL INTER COLLECT RATH, DISTT.- HAMIRPUR | 45/2016/1446/15-10-2016-33(4)/2014 Dt. 15-06-2016 | 385 | 100 | 100
41 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL LAMAURA, DISTT.- MAHOBA | 2587-90/2016-17 Dt. 24-03-2017 | 40 | 100 | 57
42 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL SHIVHAR, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
43 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL RAWATPURA KHURD, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
44 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL MAJHGUWA KHURD, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
45 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL MUHARI, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 26 | 100 | 37
46 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL SUPA, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 55 | 100 | 80
47 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL JYORAIYA, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
48 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL KULKUWAN, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 94
49 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL RIWAI SUNAICHA, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
50 | चिकित्सा एवं स्वास्थ्य सेवाएं | CONSTRUCTION OF PRIMARY HEALTH CENTRE AT VILLAGE-BASAIYA KHERA ,PADHOLIYA, DISTT- BADAUN | 182/2020/1014/5-6-2020-8(NIRMAN)/20 DATE-10.08.2020, AMOUNT- 183.99 | 47 | 47 | 26
51 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL SINGHANPUR BHAGHARI, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
52 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL BIJRARI, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
53 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL NAIPURA, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
54 | माध्यमिक शिक्षा/बेसिक शिक्षा | GOVERNMENT HIGH SCHOOL SILALPURA, DISTT.- MAHOBA | 100-103/2016-17 Dt. 22-04-2016 | 70 | 100 | 100
55 | चिकित्सा एवं स्वास्थ्य सेवाएं | DISTRICT FEMALE HOSPITAL MAHOBA | 145/2018/1012/5-6-18-15 NIRMAN/16 Dt. 28-03-2018 | 739 | 100 | 100
56 | चिकित्सा एवं स्वास्थ्य सेवाएं | GOVERNMENT HOMEOPATHIC HOSPITAL MANIKPUR AT DISTT.- CHITRAKOOT | 1240/96-AYUSH-36(B)/2018 T.C.- 1 DT. 05-08-2019 | 30 | 96 | 96
57 | चिकित्सा एवं स्वास्थ्य सेवाएं | GOVERNMENT HOMEOPATHIC HOSPITAL KABRAI AT DISTT.- MAHOBA | 1240/96-AYUSH-36(B)/2018 T.C.- 1 DT. 05-08-2019 | 30 | 100 | 100
58 | चिकित्सा एवं स्वास्थ्य सेवाएं | GOVERNMENT HOMEOPATHIC HOSPITAL MURWA AT DISTT.- BANDA | 1240/96-AYUSH-36(B)/2018 T.C.- 1 DT. 05-08-2019 | 35 | 100 | 100
59 | गृह | FIRE STATION BUILDING (RESIDENCE & NON-RESIDENCE) AT NARAINI, DISTT.- BANDA | 30/2019/428/6-PU-7-2019-43/2019 Dt. 09-03-2019 | 110 | 45 | 6
60 | गृह | FIRE STATION BUILDING (RESIDENCE & NON-RESIDENCE) AT ATRRA, DISTT.- BANDA | 34/2019/428/6-PU-7-2019-43/2019 Dt. 09-03-2019 | 110 | 41 | 5
61 | गृह | FIRE STATION BUILDING (RESIDENCE & NON-RESIDENCE) AT KULPAHAD, DISTT.- MAHOBA | 25/2019/428/6-PU-7-2019-43/2019 Dt. 09-03-2019 | 110 | 59 | 7
62 | गृह | FIRE STATION BUILDING (RESIDENCE & NON-RESIDENCE) AT MAU, DISTT.- CHITRAKOOT | 52/2019/428/6-PU-7-2019-43/2019 Dt. 09-03-2019 | 110 | 29 | 3
63 | गृह | FIRE STATION BUILDING (RESIDENCE & NON-RESIDENCE) AT MANIKPUR, DISTT.- CHITRAKOOT | 48/2019/428/6-PU-7-2019-43/2019 Dt. 09-03-2019 | 110 | 31 | 4
64 | गृह | FIRE STATION BUILDING (RESIDENCE & NON-RESIDENCE) AT RAJAPUR, DISTT.- CHITRAKOOT | 42/2019/428/6-PU-7-2019-43/2019 Dt. 09-03-2019 | 110 | 33 | 4
65 | अन्य सिविल कार्य | V.V. PAT GODOWN / WARE HOUSE AT DISTT.- HAMIRPUR | 869(1)/61-2018-67/3-2017(NIRMAN-3) Dt. 19-12-2018 | 126 | 39 | 39