## Sheet1
MPR Report
क्रम संख्या | विभाग का नाम | कार्य का नाम | शासनादेश संख्या एवं स्वीकृत धनराशि | अवमुक्त धनराशि | वित्तीय प्रगति | भौतिक प्रगति | अभियुक्ति
1 | चिकित्सा एवं स्वास्थ्य सेवाएं | C.H.C. KARARI AT DISTRICT KAUSHAMBI | 28/2016/2822/5-6-16-127(NI.0)/12 DATED 27.01.2016 | 446 | 100 | 80 | MAIN BUILDING STRUCTURE COMPLETE & PAINTING IN PROGRESS. TYPE-1 STRUCTURE COMPLETE & PLASTERING IN PROGRESS. TYPE-2 FIRST FLOOR BRICK WORK COMPLETE. TYPE-4 FIRST FLOOR SLAB & BRICK WORK COMPLETE. NALKOOP & BORING COMPLETE.
2 | चिकित्सा एवं स्वास्थ्य सेवाएं | P.H.C. SHAHPUR AT DISTRICT KAUSHAMBI | 188/2019/1320/5-6-19-26(NIRMAN)/18 DATED 15.07.2019 | 68 | 50 | 50 | BOUNDARY WALL COMPLETED & PLASTERING IN PROGRESS. MAIN BUILDING SLAB IN PROGRESS. TYPE-A STRUCTURE WORK IN PROGRESS.
3 | अन्य सिविल कार्य | ADVOCATE CHAMBER BLOCK-A, AT DISTRICT PRAYAGRAJ | 150/2017/UO36/7-NYAY-9(BAJAT)-2017-20(SAMANYA)/2013-NYAY-7 DATED 27.12.2017 | 200 | 5 | 1 | BHOOMI NOT AVAILABLE.
4 | अन्य सिविल कार्य | ADVOCATE CHAMBER BLOCK-B, AT DISTRICT PRAYAGRAJ | 02/2017/UO160/7-NYAY-9(BAJAT)-2016-20(SAMANYA)/2013-NYAY-7 DATED | 200 | 100 | 43 | BORING COMPLETED. GROUND & FIRST FLOOR WORK IN PROGRESS.
5 | अन्य सिविल कार्य | ADVOCATE CHAMBER BLOCK-C AT DISTRICT PRAYAGRAJ | 02/2017/UO160/7-NYAY-9(BAJAT)-2016-20(SAMANYA)/2013-NYAY-7 DATED | 468 | 100 | 100 | STRUCTURE WORK COMPLETED & LIFT WORK IN PROGRESS.
6 | अन्य सिविल कार्य | 04 NOS. FAMILY COURT IN DISTRICT COURT CAMPUS PRAYAGRAJ | 133/2019/1040/7-NYAY-9(BAJAT)-2019-800(40)/2016 DATED 20.09.2019 | 482 | 18 | 9 | R.C.C. COLUMN COMPLETE & SLAB IN PROGRESS OF HALF BASAMENT.
7 | श्रम विभाग (व्यावसायिक शिक्षा एवं कौशल विकास) | I.T.I. SORAON AT DISTRICT PRAYAGRAJ | 120/2015/1602/89-VYA0SHI0 & KAU0VI0VI0-2015-05(PO)/2015 DATED 05.06.2015 | 550 | 100 | 76 | MAIN BUILDING STRUCTURE WORK COMPLETED. WORK SHOP, BOUNDARY WALL, NALKOOP & O.H.T. WORK IN PROGRESS.
8 | उच्च शिक्षा | D.I.E.T. KAUSHAMBI IN RENOVATION WORK | RASHAI0/4727-40/A-1(21)/2015-16 DATED 29.04.2015 | 104 | 100 | 100 | WORK COMPLETED.
9 | उच्च शिक्षा | D.I.E.T. PRAYAGRAJ IN RENOVATION WORK | RASHAI0/4803-52/2020-21 DATED 27.03.2020 | 11 | 1 | 1 | TENDER WORK IN PROGRESS
10 | ग्राम विकास विभाग | DISTRICT PRAYAGRAJ IN VIKASKHAND KORAON RESIDENTIAL BUILDING | 27/2018/SA0/373/38-2-2018-17B/2017 DATED 22.03.2018 | 106 | 100 | 28 | TYPE-4 & TYPE-3 WORK COMPLETED.
11 | पर्यटन | SHRI BHAIRAV BABA MANDIR IN MAHEWA CHAKA NAINI, PRAYAGRAJ | 173/2018/41-2018-21(BAJAT)/2018 DATED 05.10.2018 | 52 | 100 | 100 | WORK COMPLETED
12 | पर्यटन | TEHSIL HANDIYA LAXAGRIH RENOVATION IN DISTRICT PRAYAGRAJ | 48/2019/675/41-2019-25(BAJAT)/2018 DATED 20.02.2019 | 100 | 100 | 50 | GATE WORK COMPLETED. SATSANG HALL IN PROGRESS.
13 | अन्य सिविल कार्य | TOILET & FALL CEILING IN RAJKIYA UNANI MEDICAL COLLEGE HIMMATGANJ | 14/2019/1307/96-AYUSH-1-2019-100/2019 DATED 09.03.2019 | 65 | 100 | 90 | WORK COMPLETE
14 | अन्य सिविल कार्य | 04 LECTURE HALL IN L.B.S.H. IN SHANTIPURAM PRAYAGRAJ | 14/2019/668/96-AYUSH-2-2019-11(B)/2019 DATED 08.03.2019 | 92 | 65 | 23 | FIRST FLOOR SLAB COMPLETE.
15 | अन्य सिविल कार्य | GIRL HOSTEL IN L.B.S.H. IN SHANTIPURAM PRAYAGRAJ | 14/2019/668/96-AYUSH-2-2019-11(B)/2019 DATED 08.03.2019 | 77 | 100 | 35 | THIRD FLOOR SLAB COMPLETE.
16 | अन्य सिविल कार्य | BOYS HOSTEL IN L.B.S.H. IN SHANTIPURAM PRAYAGRAJ | 14/2019/668/96-AYUSH-2-2019-11(B)/2019 DATED 08.03.2019 | 93 | 44 | 15 | GROUND FLOOR SLAB IN PROGRESS.
17 | गृह | FIRE STATION SIRATHU AT DISTRICT KAUSHAMBI | 124/2019/562/6-PU0-7-2019-83/2019/GRIH(POLICE) ANUBHAG-7 DATED 26.06.2019 | 358 | 89 | 38 | BOUNDARY WALL, MAIN BUILDING, TYPE-B & TYPE-A WORK IN PROGRESS
18 | अन्य सिविल कार्य | VETERINARY HOSPITAL AT AJUHA KAUSHAMBI | 1107/37-2-2019-(35)/2014/PASHUPALAN/DATED 18.06.2019 | 40 | 47 | 47 | MAIN BUILDING IN PROGRESS
19 | गृह | IV VAHINI PAC SEWER IN DISTRICT PRAYAGRAJ | 153/2019/1359/6-PU0-7-2019-31/2017 DATED 24.08.2019 | 320 | 100 | 50 | WORK IN PROGRESS
20 | कारागार | CONTROL ROOM IN CENTRAL JAIL NAINI PRAYAGRAJ | 60/2019/905/22-4-2019-48(16)/19 DATED 25.10.2019 | 6 | 21 | 21 | FOUNDATION WORK IN PROGRESS
21 | ऐन.ऐच.ऐम | 111 NOS. GNM CENTER IN PRAYAGRAJ | CMO/WELLNESS CENTER/NIRMAN/2019-20/5508 DATED 19.09.2019 | 380 | 90 | 50 | WORK IN PROGRESS
22 | खेलकूद/युवा कल्याण | MINI STADIUM TILGODI AT CHAIL, DISTRICT KAUSHAMBI | 456/50-YU0KA0-2020-17(GHOSANA)/2028 DATED 06.03.2020 | 125 | 4 | 1 | WORK IN PROGRESS
23 | अन्य सिविल कार्य | VIKASKHAND CHAKA NITROJAL VESEL PHENSING | 1235/37-2-2018-6(4)2018 DATED 03.04.2018 | 2 | 100 | 100 | WORK COMPLETE.